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INTRODUCTION






GRAN FONDO ISLE OF MAN

Gran Fondo Isle of Man is a major cycling event aimed at all levels of cyclist from elite riders to beginners, families and children. 

Gran Fondo Isle of Man evolved from Isle of Man Cyclefest; a wider cycling themed festival which took place successfully for three consecutive years starting in 2016. 2025 will be the final staging of the event in its current format.

In 2019, the organisers of Isle of Man Cyclefest, Isle of Man Cyclefest Ltd, decided not to produce the full festival experience for a range of personal and commercial reasons and ran a successful Gran Fondo event in its place. 

Gran Fondo Isle of Man is now organised by Gran Fondo (Isle of Man) Ltd, along with the wider organisational team who have been involved in delivering the event since the outset.

Gran Fondo Isle of Man is scheduled to take place on Saturday the 19th and Sunday the 20th of July 2025, once again based from an Event HQ at Mooragh Park in Ramsey. The event features four individual cycling events: 

Gran Fondo – The only true competitive Gran Fondo event staged in the British Isles, held on a largely closed roads 85-mile course.

Medio Fondo – A non-competitive sportive for recreational riders who want to test themselves that little bit further across this 40-mile route.

Piccolo Fondo – A non-competitive sportive aimed at families and beginners, the 20-mile route takes in the coastline and flatter farmland of the Island’s northern plains.

Minisculo Fondo - The family-friendly Minisculo Fondo, held over a half-mile circuit in and around Ramsey’s Mooragh Park is open to children, families and beginners. 


ROAD CLOSURES & TRAFFIC RESTRICTIONS 


Gran Fondo Isle of Man is an international event and the Island’s premier mass participation sporting occasion. 

Gran Fondo (Isle of Man) Ltd will professionally manage the risks to competitors and spectators when delivering this event. It is for that reason that road closures and traffic restrictions are once again requested.

The road closures have been considered in relation to usage and disruption to resident’s normal routine. 

There are a number places where road closures could have been applied for but this would mean severe disruption to the residents and gain little for the event. There has been a considered balance between what is needed for the event and what is practical for the Islands population in making these applications.

Formal and informal consultation takes place with a range of stakeholders as part of the course design process. This includes local authorities, regulatory bodies, impacted businesses, sporting associations and clubs and public transport operators.

A public relations blitz with local residents is scheduled to take place in the weeks leading up to the event to minimise the impact the event has to locals and to proactively deal with any issues and/or special arrangements that may be required to be implemented.

The organising team delivering the event and managing the road closures has extensive experience in this regard from events such as the Isle of Man TT Races and Manx Grand Prix as well as nine years' worth of experience delivering extensive road closures across the Isle of Man Cyclefest and Gran Fondo Isle of Man events.

SCHEDULE


Saturday 19th July 2025


1500hrs	Minisculo Fondo


Sunday 20th July 2025

0930hrs	UCI Gran Fondo

0945hrs	Medio Fondo

1000hrs	Piccolo Fondo






PARCOURS









MINISCULO FONDO
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ROAD CLOSURES








MINISCULO FONDO – SATURDAY JULY 19th 2025
Road Closure Time 1430hrs to 1630hrs

- Park Road

- North Shore Road from its junction with Park Road to the junction with Ballacloan Road

- Ballacloan Road















GRAN FONDO | MEDIO FONDO | PICCOLO FONDO – SUNDAY JULY 20th 2025

SECTOR 1 
Road Closure Time 0830hrs to 1200hrs

- A10 Bride Road from its junction with Mooragh Promenade to the junction with Lamb Hill.

- Lamb Hill.

- A10 Bride Road from its junction with Cranstal Road to the junction with Bretney Road.

- Ballavarran Road.

- Jurby Road from its junction with Ballavarran Road to the junction with the A14.

- The A14 from its junction with Jurby Road to the junction with Ballaugh Curragh’s.

- The Ballaugh Curragh’s from its junction with the A14 to the junction with Old Windmill Road

- Old Windmill Road from its junction with the Ballaugh Curragh’s to its junction with Dollagh Mooar Road

- The Dollagh Mooar Road from its junction with Old Windmill Road to its junction with Ballaterson Manor.

- Ballaterson Manor.
SECTOR 2
Road Closure Time 0930hrs to 1300hrs


- Glen Road.

- Druidale Road

- Beinney Phott Road (closed till 1600hrs).

- Sartfield Road.

- Little London.

- Ballabooie Road from its junction with the A3 to the junction with Staarvey Road.

- Staarvey Road.

- Switchback Road from its junction with Staarvey Road to the junction with the A20 Poortown Road.






SECTOR 3
Road Closure Time 1000hrs to 1500hrs

- Station Road.

- Patrick Road from its junction with Station Road to the junction with the A27 Dalby Road.



SECTOR 4
Road Closure Time 1000hrs to 1500hrs

- A27 Dalby Road from its junction with Lhagg Road to the junction with the A36 Round Table Road.

- A27 Ronague Road from its junction with the A36 Round Table Road to the junction with Corlea Road.

- Corlea Road from its junction with the Ronague Road to the junction with the west side of South Barrule Plantation.

- Glen Rushen Road from its junction with the A36 Round Table Road to the junction with Slieau Whallian Road.

- Slieau Whallian Road.

SECTOR 5
Road Closure Time 1100hrs to 1600hrs

- Ballavargher Road from its junction with Slieau Whallian Park to the junction with Archallagan Road.

- Archallagan Road.

- Old Church Road.

- West Baldwin road from its junction with Ballamodha Road to Beinn-y-Phott Road

- Beinney Phott Road (closed from 0930hrs).

SECTOR 6
Road Closure Time 1030hrs to 1700hrs


- A14 Tholty Will Road from its junction with the A18 Mountain Road to the junction with the Sulby Claddagh’s

- St Jude’s Road. 




SECTOR 6
One Way System Time 1030hrs to 1700hrs

- Sulby Claddaghs (Yn Claddagh) from its junction with the A14 Tholty Will Road to the junction with the A3 Lezayre Road.
SECTOR 7
Road Closure Time 1000hrs to 1700hrs


- A13 Jurby Road from its junction with St Jude’s Road to the junction with Westhill Village.

- A13 Jurby Road from its junction with Ash Grove to the junction with Bowring Road.

- Bowering Road from its junction with Coburg Road and Grove Mount South.

- Cumberland Road

- Windsor Mount Road.







TRAFFIC MANAGEMENT PLAN
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GRAN FONDO SECTOR 1
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GRAN FONDO SECTOR 2
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GRAN FONDO SECTOR 3
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GRAN FONDO SECTOR 4
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GRAN FONDO SECTOR 5
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GRAN FONDO SECTOR 6
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GRAN FONDO SECTOR 6 (SULBY CLADDAGHS 1 WAY SYSTEM)

[image: ]
GRAN FONDO SECTOR 7
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GRAN FONDO SECTOR 7 (BOWRING ROAD DIVERSION)
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RISK ASSESMENT








	Gran Fondo Isle of Man comprises five organised cycle events on Saturday 19th and Sunday 20th July 2025.

	The events are graded for different levels of cycling ability from children and beginners to professional cyclists.

	 
	
Individual Time Trial  
Minisculo Fondo
	Beginners, children and accompanying adult cyclists ride a track around the Mooragh Park

	 
	Gran Fondo
Medio Fondo
	Experienced regular cyclists – mix of competitive and recreational riding a challenging 85 Mile course
Experienced and intermediate cyclists ride a 40 Mile course

	 
	Piccolo Fondo
	Intermediate and casual cyclists ride a 20 Mile course

	 
	
	

	Hazard
	Who
	Impact
	Risk Rating
	Control Measures
	Residual Risk

	General Traffic
	Riders
	Collision / injury
	HIGH
	Close Road where practical to maintain separation of riders from traffic
	MED

	
	Competitors
	
	
	Course inspection vehicle to check route ahead of cyclists
	

	
	Setup Team
	
	
	Set-up / break-down teams to wear hi-vis clothing when out of vehicle
	

	
	Marshals
	
	
	Vehicle to use hazards warning lights when stopping for setup/breakdown
	

	
	Travelling marshals
	
	
	Adequate event signage and support vehicle labelling
	

	
	
	
	
	
	

	
Junctions
	
	
	
	
	

	Type A with private access route
	All as above
	Collision / injury
	MED
	Mail drop; Direct communication with residents; Course inspection; Road closed signs only if required.
	LOW

	Type B with low use road / green lane
	All as above
	Collision / injury
	MED
	Road closed sign only
	LOW

	Type C with medium use road
	All as above
	Collision / injury
	MED
	Road closed sign with attending marshal(s) as required
	LOW

	Type D with high use or high speed road
	All as above
	Collision / injury
	HIGH
	Road closed sign with marshal(s); travelling marshal to assist as necessary
	LOW

	Type E open road with traffic flow
	All as above
	Collision / injury
	HIGH
	Marshal(s) with travelling marshal as necessary
	MED

	Type F open road crossing traffic flow
	All as above
	Collision / injury
	HIGH
	Marshal(s) with police assistance and /or travelling marshal as necessary
	MED

	
	
	
	
	
	

	
	
	
	
	
	

	Pedestrians within Mooragh Park
	Riders/competitors and pedestrians
	Collision / injury
	HIGH
	Barriers as necessary; Marshal(s) with audible warning devices attending crossing points
	MED

	
	
	
	
	
	

	Emergency response vehicle access
	All as above
	Collision / injury
	MED
	Race control will be in contact with control room and with support vehicles and Travelling Marshals via the digital radio system to warn and co-ordinate for any emergency vehicles, which have to enter the closed roads.
	LOW

	
	
	
	
	
	

	Route goes from closed to open road
	All as above
	Collision / injury
	HIGH
	Signage, marshals, travelling marshals and police as required
	LOW

	
	
	
	
	
	

	Vehicle follows riders from open to closed roads
	All as above
	Collision / injury
	MED
	Signage, marshals, travelling marshals and police as required
	LOW

	
	
	
	
	
	

	Adverse Weather
	All as above
	Loss of visibility leading to collision / injury
	HIGH
	Commissaires to advise on viability of route during event
	MED

	
	
	
	
	
	

	Riders going off route
	Riders/Competitors
	Riders potentially unsafe
	HIGH
	Rider briefings, support vehicle communications and transponder sector tracking
	LOW

	
	
	
	
	
	

	
	
	
	
	
	

	Road surface faults
	All as above
	Crash / injury
	HIGH
	Request to DoI Highway Services to patch and pre-sweep route. Warning signs for riders
	MED

	
	
	
	
	
	

	Slow riders
	Riders/Competitors
	Closure finishes and rider proceeds on open roads
	MED
	Communications through rider information packs, rider briefings, and road open vehicle to notify any riders it overtakes
	LOW

	
	
	
	
	
	

	Retirements from event
	Riders/Competitors
	Rider unaccounted for
	MED
	Rider briefings, support vehicle communications and contact number at race control
	LOW

	
	
	
	
	
	

	General Injuries
	All as above
	As hazard 
	MED
	First aid and paramedic support
	LOW

	
	
	
	
	
	

	‘Problem’ junctions (Crosby, St Johns, Garth)
	Riders/Competitors
	Crash / Injury
	MED
	Increased signage and increased marshals and stewards to be deployed.
	LOW

	
	
	
	
	
	

	Participant crashes
	Riders
	Injury
	HIGH
	MRMS engaged to provide robust medical response built from previous learning’s on event. Controlled and managed from central Race Control with direct links to IOM NHS.
	MED

	
	
	
	
	
	

	Weather
	Riders
	Crash / Injury
	HIGH
	Riders advised of consequences of extreme weather in days before event and at pre-race briefing. Broom wagon to follow the race at the back of the convoy to pick up riders who may be affected by adverse weather and will have suitable clothing made available. All personnel assisting with the event to be advised in advance of the predicted weather forecast and advised to be dressed appropriately
	MED

	
	
	
	
	
	

	Fatigue/dehydration
	Riders/Competitors
	Crash / injury
	MED
	Provide feeding stations and water pick-up points
	LOW




KEY CONTACTS / INFORMATION



Event Director			Paul Phillips		07624480451		paulphillips@manx.net

Clerk of Course			Lizzie Kinvig		07624298608		lizziekinvig@gmail.com

Web Site	 			granfondoisleofman.com

Facebook				facebook.com/granfondoiom

Instagram				www.instagram.com/granfondoiom
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